## Sheet1
Ecclesfield Parish Council Annual/Project Plan 2022-2023 - Update Jan 23
Main Activity* | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | feb | Mar | Apr | Traffic Light | Budget | Notes
Parish Survey | [13 empty] | 10000 | At is November 2022 meeting it agreed to not progress this activity
RBL, Schools and Bloom Groups Grant | [13 empty] | 5750 | bar: Oct to Dec
Improvements to Council Offices | [13 empty] | 10000 | bar: Jul to Aug
Neighbourhood Plan | [13 empty] | 20000
Parish Newsletter | [13 empty] | 2000 | bar: May; Aug; Nov; Jan
Finance Leaflet | bar: May
Community Hall Refurbishment | [13 empty] | 50000 | bar: May to Jun
Notice Board Improvements | [13 empty] | 5000 | bar: May to Jun
Park Bench Improvements | [13 empty] | 6000
Time capsules
Jeffcock Road Survey | [13 empty] | 0 | bar: May to Jun
Queens Platinum Jubilee Celebrations | [13 empty] | 2500 | bar: May to Jun; Oct to Nov
Lump Lane Legal Advice | [13 empty] | 2500 | bar: May to Jun
Archiving Project | [13 empty] | 8350
Remembrance Events | [13 empty] | 0 | bar: Oct to Nov
Annual Governance and Accountability Return | [13 empty] | 1000 | bar: May to Jul
External & Internal Audit/AGAR (including interim) | bar: May to Jun; Oct to Nov
Budget setting for 2023/2024 | [13 empty] | 0 | bar: Oct to Nov
Covid Monuments (individual parks) | [13 empty] | 0 | bar: Jun to Aug
Walkin Posts | [13 empty] | 5000 | bar: May to Jul
Upgrade fire alarm/security systems at Council offices | [13 empty] | 2000 | bar: Jan to Apr
Community Environment days | bar: Jul to Aug
No Mow May | bar: May
Environmental/wilding cameras in schools
Keep Our Parish Tidy Spring Clean | bar: Mar to Apr
Gardening Competition | [13 empty] | 0 | bar: May to Jul
Meals for the isolated - with Chapelgreen Hub | [13 empty] | 0 | bar: Nov; Apr
War Heroes Project
Hampers for families in need - with Chapelgreen Hub | bar: Nov; Apr
School Uniform Swap shop | [13 empty] | 1000
School Uniform swap shop open days | bar: Jul; Apr
Community Skip Days | [13 empty] | 2000 | bar: May to Jul
Plastic Free Parish | bar: Jul to Apr
Angram Bank Survey Feedback | [13 empty] | 0 | bar: Jun
Repairs to Chapletown Toilets | [13 empty] | 3300 | bar: May to Jun
ASB/Alan Greaves Project | [13 empty] | 10000 | bar: Oct to Apr
Tender and Appoint new External Auditor | bar: Nov to Dec
Ukrainian Humanitarian Project | [13 empty] | 750 | bar: Nov; Jan to Apr
*Only key ones (other more routine/operations ones are not included)
Other
Main Activity* | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | feb | Mar | Apr | Traffic Light | Budget
Grenoside Exhibition Foundation Charity to become separate from the Parish Council | [13 empty] | All costs to be met by the Foundation